## 01_Project_Overview
Category | Target | Description | Priority | Status
Core Goal | NLP Fake News Dectection | Analyze textual claims and predict their credibility/veracity class | Critical | Planned
MVP | End to end prediction | User input → backend → preprocessing → model → prediction → result | Critical | Planned
Main Target | Complete NLP application | Compare models, select suitable model, integrate backend/database/frontend and evaluate system | High | Planned
Explainability | Prediction Explaination | Provide interpretable information about model predictions where practical | Medium | not planned
Future Target | Evidence based Fact Checking | Retrieve external evidence and generate evidence-backed assessments | Future | not planned

## 02_Methodology
Field | Value
Methodology | Agile – Iterative & Incremental Development
Project Type | NLP / Machine Learning + Web Application
Sprint Duration | 1 week
Development Style | Experiment → Evaluate → Improve → Integrate
Version Control | Git + GitHub
Current Stage | Dataset Understanding
Primary Dataset | LIAR
Final Target | End-to-end Fake News Detection application
Development stages |  |  | Definition of Done
Stage | Main Activity | Expected Output | Work Type | Considered Done When
1. Planning | Define requirements, scope, architecture and tasks | Project plan & backlog | Dataset Task | Analysis/preprocessing completed, checked and documented
2. Dataset Understanding | Study LIAR attributes, labels, distributions and limitations | Dataset analysis | ML Experiment | Model trained, metrics recorded and result reproducible
3. Data Preprocessing | Clean and transform textual/metadata features | Reusable preprocessing pipeline | Feature | Implemented, tested and integrated
4. Baseline Modeling | Train traditional NLP/ML models | Baseline performance | Backend/API | Endpoint works and required errors are handled
5. Advanced Modeling | Experiment with Transformer-based models | Advanced model results | Database | Schema implemented and tested with application
6. Evaluation | Compare models using appropriate metrics | Model comparison | UI | Functional and connected to required backend functionality
7. Model Selection | Select a suitable model considering quality and deployment constraints | Deployment candidate | Documentation | Written, reviewed and updated to match implementation
8. Backend Development | Develop APIs and model-serving logic | Working backend
9. Database Integration | Store required users/results/history/data | Integrated database
10. Frontend Development | Build user interface | Working UI
11. Integration | Connect frontend, backend, model and database | Complete application
12. Testing | Model, API, integration and system testing | Tested system
13. Documentation | SRS, diagrams, experiment records, report | Project documentation
14. Review & Improvement | Evaluate shortcomings and improve the system | Final release

## 03_Sprints
Sprints |  |  |  | Detailed Sprints Overview
Sprint | Duration | Primary Goal | Main Deliverable | Sprint ID | Sprint Name | Start Date | End Date | Duration | Sprint Goal | Deliverables | Status | Progress %
Sprint 0 — Planning | Before development | Finalize scope, methodology, datasets, architecture, backlog and environment | Project plan | S0 | Planning | 2026-10-29 | — | Pre-project | Finalize project plan | Scope, methodology, backlog, architecture | In Progress | —
Sprint 1 — Data & Baseline | Week 1 | Understand/preprocess LIAR and establish traditional ML baselines | Reproducible baseline models | S1 | Data & Baseline | — | — |  | Build data pipeline and baseline | Preprocessed data + baseline results | Not Started | 0%
Sprint 2 — Advanced NLP | Week 2 | Develop and evaluate stronger NLP/Transformer approaches | Advanced model + model comparison | S2 | Advanced NLP | — | — |  | Develop stronger NLP models | Advanced model + comparison | Not Started | 0%
Sprint 3 — Application Development | Week 3 | Build backend, database and frontend; serve selected model | Working end-to-end application | S3 | Application Development | — | — |  | Build complete application | Frontend + backend + DB + model integration | Not Started | 0%
Sprint 4 — Integration & Finalization | Week 4 | Testing, improvements, explainability, documentation and final integration | Submission-ready project | S4 | Integration & Finalization | — | — |  | Make project submission-ready | Tested application + documentation | Not Started | 0%
"IDEAL" Date-wise Work Distribution
Phase | Dates | Duration | Main Goal
Sprint 0 – Planning | 29 Sep – 4 Oct | ~6 days | Planning, requirements, dataset understanding, environment
Sprint 1 – Data & Baselines | 5 – 11 Oct | 7 days | Preprocessing + baseline ML models
Sprint 2 – Advanced NLP | 12 – 18 Oct | 7 days | Advanced NLP/Transformer models + evaluation
Sprint 3 – Application | 19 – 25 Oct | 7 days | Backend + database + frontend + model integration
Sprint 4 – Finalization | 26 – 29 Oct | 4 days | Testing, explainability, fixes, documentation
Submission Buffer | 30 – 31 Oct | 2 days | Final checks, packaging, report/PPT/demo preparation
Deadline | 2026-11-01 | — | Final submission

## 04_Learning_tracker
Learning Tracker
Topic | Needed For | Priority | Learn By | Status | Confidence
NLP fundamentals | Entire project | Critical | Sprint 1 | — | —
Text preprocessing | Data pipeline | Critical | Sprint 1 | — | —
TF-IDF | Baseline | Critical | Sprint 1 | — | —
Logistic Regression | Baseline | High | Sprint 1 | — | —
Evaluation metrics | Model evaluation | Critical | Sprint 1 | — | —
Transformers | Advanced model | High | Sprint 2 | — | —
BERT architecture | Advanced model | High | Sprint 2 | — | —
REST APIs | Backend | High | Sprint 3 | — | —
Model serving | Integration | High | Sprint 3 | — | —

## 05_Project_Backlog
Backlog
Task ID | Epic | Task | Description | Sprint | Priority | Owner | Status | Start Date | Due Date | Dependency | Deliverable | Notes
Note on B2: Neo _: What is an Epic? An Epic is a large piece of work that is too big to complete as a single task, so we break it into smaller tasks. Think of the hierarchy as: Project → Epic → Tasks For our project: PROJECT Fake News Detection using NLP ↓ EPIC Dataset & Data Analysis ↓ TASKS ├── Download/setup LIAR dataset ├── Understand all LIAR attributes ├── Add column names ├── Analyze missing values ├── Analyze label distribution ├── Analyze statement lengths └── Document dataset findings

## 07_TechStack
Technology Stack
Category | Requirement | Selected Technology | Alternatives Considered | Purpose | Reason for Selection | Learning Required | Status | Notes
Programming Language | Main development language | Python | - | Primary language for data processing, NLP, ML and backend | Strong ML/NLP ecosystem and already familiar with Python | Low | Selected
Data Processing | Dataset manipulation | Pandas | Polars | Load, clean, transform and analyze datasets | Mature ecosystem and well suited for LIAR-sized tabular datasets | Low | Selected
Numerical Computing | Array and numerical operations | NumPy | - | Numerical operations and array manipulation | Standard numerical library used throughout Python ML ecosystem | Low | Selected
Data Visualization | EDA and result visualization | Matplotlib | Seaborn | Visualize dataset distributions, model results and evaluation metrics | Simple, flexible and integrates well with Pandas | Low | Selected
Traditional Machine Learning | Baseline ML models | Scikit-learn | - | Feature extraction, baseline models, pipelines and evaluation | Provides TF-IDF, classical ML algorithms and evaluation utilities in one ecosystem | Medium | Selected
Text Feature Extraction | Traditional NLP feature representation | TF-IDF (Scikit-learn) | Bag of Words | Convert text into numerical features for baseline models | Strong and interpretable baseline for text classification | Medium | Selected
Deep Learning Framework | Train deep learning/Transformer models | PyTorch | TensorFlow | Training and fine-tuning neural NLP models | Widely used with modern NLP and Hugging Face ecosystem | High | Selected
Transformer Ecosystem | Pretrained NLP models | Hugging Face Transformers | Direct PyTorch implementations | Tokenizers, pretrained Transformer models and fine-tuning | Simplifies working with pretrained Transformer architectures | High | Selected
NLP Utilities | Text preprocessing | Not Decided | NLTK, spaCy | Text tokenization and other preprocessing operations | Exact preprocessing requirements should be determined after dataset analysis | Medium | Researching
Model Explainability | Explain model predictions | Not Decided | SHAP, LIME, model-specific methods | Provide interpretable information about predictions | Depends on final deployed model | High | Not Decided
Backend Framework | Model-serving/API backend | Not Decided | FastAPI, Flask, Django | Expose trained model through application API | Should be selected after backend requirements are finalized | Medium | Not Decided
Database | Persistent application storage | Not Decided | MySQL, PostgreSQL | Store application data, prediction history and related records | Database requirements still need to be finalized | Medium | Not Decided
Frontend | User-facing interface | Not Decided | HTML/CSS/JavaScript, React, Streamlit | Allow users to submit claims and view results | Depends on desired application complexity and available development time | Medium | Not Decided
API Communication | Client-server communication | REST API | - | Connect frontend with backend prediction service | Simple and appropriate for prediction request/response workflow | Medium | Selected
Model Persistence | Save/load trained models | Not Decided | joblib, pickle, PyTorch checkpoints, Hugging Face save_pretrained | Store trained models for later inference | Depends on final model type | Low | Not Decided
Version Control | Source code versioning | Git | - | Track code changes and development history | Industry standard and already familiar | Low | Selected
Repository Hosting | Remote source repository | GitHub | GitLab | Store and manage project repository | Integrates easily with Git and already familiar | Low | Selected
Development Environment | Main coding environment | VS Code | PyCharm, Spyder | Code development, debugging and Git integration | Already familiar and suitable for full-stack Python development | Low | Selected
Experiment Environment | Exploratory ML development | Jupyter Notebook | VS Code scripts, Google Colab | EDA, experimentation and model analysis | Interactive workflow is convenient for ML experimentation | Low | Selected
Cloud Compute | Optional model training | Google Colab | Kaggle Notebooks | Local machine | Access GPU resources if Transformer training is expensive locally | Useful if local hardware is insufficient | Not Decided | Selected as Needed
API Testing | Backend endpoint testing | Not Decided | Postman, FastAPI Swagger UI | Test requests, responses and error handling | Depends on selected backend framework | Low | Not Decided

## 08_Datasets
Datasets Information
Dataset ID | Dataset Name | Dataset Type | Primary Purpose | Content Type | Role in Project | Planned Sprint | Status
DS-01 | LIAR | Claim-level fact-checking dataset | Main training/evaluation dataset | Short statements/claims | Primary Dataset | S1–S2 | Available
DS-02 | FakeNewsNet | News/social-context dataset | Potential supplementary experiments | News + social/contextual information | Supplementary Dataset | Future / TBD | Available
DS-03 | Full-Article Dataset | Article-level fake-news dataset | Full-news/article experiments | Full news articles | Supplementary Dataset | Future / TBD | Available

## 06_Milestones
Milestone Tracker
Milestone ID | Milestone | Target Date | Sprint | Success Criteria | Status | Completion Date | Notes
Note on F2: Neo _: What is "Success Criteria"? This is important. A milestone shouldn't just have a name; we need a way to objectively decide whether we've reached it. For example: ¦ Milestone ¦ Bad success criterion ¦ Better success criterion ¦ ¦ Dataset Ready ¦ Worked on dataset ¦ Dataset understood, cleaned and preprocessing pipeline working ¦ ¦ Baseline Complete ¦ ML model trained ¦ Selected baseline models trained and evaluation metrics recorded ¦ ¦ MVP Complete ¦ Website created ¦ User can enter claim and receive model prediction through complete application ¦